OECD / OPSI — ARTE (Portugal)

BinaryVoice

MVP Development Report

Matriz para a Avaliação nos Serviços Públicos

Reporting period: 28 June – 24 July 2026

Report date: 27 July 2026  ·  Prepared by David Cruz (BinaryVoice), technical development lead

1. Executive Summary

This report describes where the Matriz para a Avaliação nos Serviços Públicos platform stands today, covering the full development period from 28 June to 24 July 2026: turning the approved Figma design (“Matrix Prototype v3”) into a working website connected to a live database, now in use by five public entities — ARTE, the Tax and Customs Authority (AT), the Institute of Social Security (ISS), Lisbon City Council (CML), and the Agency for Development and Cohesion (AD&C).

Where things stand, in summary:

- Twelve screens from the Figma design have been turned into a working website: choosing an entity, viewing all 9 evaluation dimensions, browsing indicators in detail, browsing services, a dashboard, an innovation-resources section, and a search feature.

- The platform’s core structure — 9 evaluation dimensions — is finalised, and every dimension now has indicators assigned to it. This fixes an early mismatch between the Figma design and the first data sample, where two dimensions had no indicators at all.

- Real data has been loaded for all five entities, covering user-experience, operational, and compliance information. Compliance data now covers all 43 official indicators for four of the five entities (CML, AD&C, ISS, ARTE).

- A password is now required to access the platform: one shared password for everyone, checked securely, never stored anywhere in a readable form.

- A new page, Panorama Estratégico, gives OCDE/ARTE a first side-by-side view comparing all five entities at once.

- The client’s first formal round of testing feedback (15 July) has been fully addressed (Section 2).

- Two data problems were found and fixed during development: one had been silently hiding some indicators from view, and the other had scored one compliance indicator the wrong way round for every entity.

## How mature is the platform right now?

## This report rates three areas of the platform against OECD’s own December-2025 roadmap for the project, using three simple levels:

- Low — just starting out on this particular step of the roadmap.

- Intermediate — clearly past the basics, meeting most (but not all) of the roadmap’s next step up.

- Advanced — meeting OECD’s most advanced criteria for this area.

| Area | Rating | Why |
| --- | --- | --- |
| Data | Intermediate | Real data now covers most of what’s needed across the five entities; loading it is AI-assisted, with a person checking and approving every step, rather than a fully self-service process (Section 3.3). |
| Design and Technology | Intermediate | Design-standard compliance and a full accessibility review are now complete; a password protects the platform, but everyone still shares one login with identical access (Section 4.5). |
| Capabilities and Features | Intermediate | Most planned features work end-to-end; a handful (favourites, automatic alerts, AI-assisted analysis) are still missing (Section 5.5). |

2. Scope of This Development Cycle

The project follows a phased approach agreed with OECD/OPSI. The first phase — reviewing the Figma design, defining the data structure, and agreeing the technical approach — is complete. The platform is now formally in the front-end build phase, working from the approved design and data structure, though work on loading real data began early (8 July) and has continued since.

## What was delivered

- Twelve pages from the Figma design turned into a real, working website, with support for five different entities — each one sees and works only with its own data.

- The 9 evaluation dimensions finalised and fully populated with indicators, including two dimensions — Information Security & Open Data and User Engagement — that started out with none at all.

- All dummy/placeholder data has been found and removed from the database. Nothing fabricated remains anywhere: every entity, service, and indicator that has data today is backed entirely by real, client-provided information.

- Real data loaded for all five entities: user-experience survey results, some operational data (including footfall/demand figures, and service-desk data for ARTE and AT), and compliance data — now complete, across all 43 official indicators, for four of the five entities.

- A password now required to use the platform (Section 4.2).

- Panorama Estratégico — a new, separate page giving a side-by-side comparison across all five entities (a heatmap, a data-coverage view, an indicator comparison, and a data-collection maturity view) — see Section 5.1.

- The client’s first formal round of testing feedback (15 July) fully addressed — see the table below.

- Two data problems found and fixed: one compliance indicator scored the wrong way round for every entity, and a second issue that was silently hiding some indicators from view (both explained in Section 3.2).

- Smaller usability fixes: the “Change Service” button on the indicator page, which previously had no effect, now works; and the 1–5 rating gauge was resized with tidier labels for readability.

## Response to the 15 July testing feedback

## The client’s first formal feedback document (15 July) framed most items as clarifications of existing requirements rather than new requests. The table below shows what is verifiably in the current build against each item raised.

| Client feedback item | Current status |
| --- | --- |
| Always display all 9 dimensions, flagging those without data | Done — dimensions always show, with a clear message when there’s no data |
| Finalize dimension names and definitions per the client’s table | Done — updated across the whole platform |
| Add Innovation to the main menu | Done — now shown in the sidebar for everyone |
| Remove a duplicate ARTE indicator in the Simplicity dimension | Done — the duplicate was removed |
| A way to switch between overall vs. per-channel views, and one service vs. all services | Done — added as a dropdown at the top of the screen |
| Rename the “Obrigatórios” filter to “Indicador da Matriz” | Done — label updated |
| Add an Innovation Resources button ahead of the external OPSI link | Done — new item added to the Innovation page |
| Link the Innovation Booster/Accelerator to somewhere useful | Done — links out to the external toolkit |
| Add a filter for Matrix-adoption status on the Indicators page | Done — filter added |

## Explicitly out of scope

- Letting entities upload their own data directly — deprioritized for this delivery due to the tight timeline, by agreement with OCDE/ARTE; data continues to be loaded through the AI-assisted process described in Section 3.2, checked and approved by a person at every step, rather than through a self-service upload.

- Favourites/bookmarks and Export/Share/Compare (on the indicator page) — deprioritized for this delivery due to the tight timeline, by agreement with OCDE/ARTE.

- Different types of user accounts — the password is shared by everyone; there are no individual logins or different permission levels yet.

- “Os Meus Serviços” — out of scope. This is not a feature that exists in the current build, and it is not part of the approved scope of this delivery.

Every screen on the platform is backed entirely by real or client-provided data — no invented or placeholder data remains anywhere on the platform.

3. Data

## 3.1 Data Coverage and Collection

## Five entities are live on the platform. How much real data is available differs between them, depending on what each has been able to provide so far:

| Entity | User Experience | Operational | Compliance |
| --- | --- | --- | --- |
| ARTE (Agency for the Technological Reform of the State) | Real — original survey data | Real (partial) — footfall/demand figures, plus new service-desk data (footfall, drop-offs, waiting and service times, ratings) | Real — all 43 official indicators |
| AT (Tax and Customs Authority) | Real — same survey as ARTE | Real (partial) — footfall/demand figures, plus new service-desk data | Not yet available — the one entity that hasn’t submitted compliance data yet |
| ISS (Institute of Social Security) | Real — dedicated multichannel survey | Real (partial) — footfall/demand figures only | Real — all 43 official indicators |
| CML (Lisbon City Council) | Real for 3 of 5 services; 2 not yet submitted | Real for 3 of 5 services; 2 not yet submitted | Real — all 43 official indicators |
| AD&C (Agency for Development and Cohesion) | Real — dedicated survey, 108 usable responses | Not available — AD&C hasn’t provided operational data | Real (self-reported), applied at entity level to both services |

## Note: compliance answers are collected once per entity through a questionnaire — the same answers apply across all of that entity’s services, as is already the case for AD&C, rather than being collected separately for each service. Two evaluation dimensions — Information Security & Open Data and User Engagement — now have real answers for the four entities with complete compliance data.

## Note on AT: the list of AT services used in testing so far may no longer match the services planned for the next round; this needs to be confirmed with AT, and is made more pressing by AT still being the only entity without real compliance data.

## 3.2 Data Quality and Validation

- Loading real data is semi-automatic and AI-assisted: each file the client sends is analysed and, where needed, reworked with AI assistance (using Claude Code), which then carries out the actual loading into the platform — but a person checks and approves every step, rather than the AI acting on its own.

- Anything unexpected or unclear in a source file — such as an unusual survey answer — is flagged for that person to check, rather than being guessed at or silently dropped.

- Every batch of new data is recorded step by step, so there is a full, traceable history of what was loaded, when, and from which file.

- Duplicate or inconsistent service names found across different source files were spotted and merged during loading, rather than left as accidental duplicates.

- One real example of this checking process at work: one compliance indicator (about interoperability, where a lower value is actually the better result) had been scored backwards for every entity since it was first introduced. This was only caught once ISS — the first entity with a genuine answer for that indicator — submitted its data, and was then corrected everywhere it appears on the platform.

- This confirms the checking process works, but also confirms that getting the scoring direction right for each indicator is a real, recurring risk worth double-checking on every future batch of indicators.

- There is no placeholder or invented data anywhere on the platform: wherever data hasn’t been submitted yet (Section 3.1), the platform shows this honestly as missing, rather than filling the gap with a fabricated value.

## 3.3 Maturity Assessment – Data

Maturity rating: Intermediate - OECD’s December-2025 starting point for data collection was “some indicators covered.” - Four of five entities are now past the next step up: all 43 compliance indicators, plus real or partly-real user-experience and operational data. - Not yet full coverage everywhere — AT hasn’t submitted compliance data yet, CML has two services that haven’t submitted user-experience or operational data, and AD&C hasn’t provided operational data. - The bigger gap is process, not data: loading data is AI-assisted (Section 3.2), which is faster and more consistent than fully manual work, but it still needs a person to check and approve every step, and there is no self-service way for entities to submit data themselves — this is what keeps the rating at Intermediate rather than higher.

4. Design and Technology

## 4.1 Platform and Architecture

- The website is built with modern, mainstream, actively-supported web technology (Next.js, React, and TypeScript, styled with Tailwind CSS) — a standard, well-understood choice, not a one-off or unusual one.

- Data is stored in Supabase, a managed cloud database service. The website itself can only read data — it cannot change anything directly; all data changes happen separately, through the controlled loading process described in Section 3.

- Each entity’s data is kept in its own separate, isolated part of the database rather than all mixed together, which is why the indicator-visibility fix (Section 3.2) had to be applied separately for each entity.

- The website is hosted on Railway, and the code is stored on GitHub — both currently under accounts owned by BinaryVoice, not by ARTE or OCDE. This is now an explicit, open question that has been shared with ARTE in writing (see docs/Handover — Technology Stack and Requirements for ARTE.docx); it is carried into Section 6 and Appendix A.

## 4.2 Access and User Profiles

- A password is now required to use the platform (except the login page itself). It is one shared password, checked securely on our servers — never stored anywhere as plain, readable text, only as a scrambled version that can’t be reversed.

- Once someone logs in, they stay logged in for 30 days, so they are not asked for the password on every visit.

- If the password is not set up correctly behind the scenes, the system blocks access rather than letting people in by mistake.

- This is a first, basic layer of protection, not a full user-account system: everyone who has the password sees exactly the same thing, with no individual logins and no different levels of access between people.

- Choosing an entity on the platform only changes which data is shown — it does not identify who the person is or what they are allowed to do.

## 4.3 Accessibility and Design Standards

- The platform now fully complies with the Ágora Design System (the Portuguese government’s design standard) for colours, fonts (Noto Sans), and icons. Interactive components — buttons, cards, filters, and so on — are custom-built using those colours, fonts, and icons as a foundation, rather than Ágora’s official ready-made building blocks: a deliberate, agreed choice, not a compliance gap.

- A full accessibility review has now been completed, covering WCAG and European Accessibility Act requirements — including using the platform with only a keyboard, and with a screen reader for blind or low-vision users.

- Throughout the platform, status is always shown with both an icon and a colour together (for example in the compliance overview, KPI changes, and ranking flags), not colour alone — which is good practice for colour-blind users.

## 4.4 Performance and Usability

- No formal testing has been done to see how the platform behaves under heavy use; this is acceptable given the current assumption of only 1–5 people using it at a time during this phase.

- The Dashboard is built to keep working smoothly as the amount of data grows, by fetching it in manageable batches rather than all at once.

- The “Change Service” button on the indicator page, which previously had no effect, now works correctly; the 1–5 rating gauge was resized with tidier labels for readability.

## 4.5 Maturity Assessment – Design and Technology

Maturity rating: Intermediate - OECD’s roadmap sets two conditions for the next step up on access and user profiles: a basic website with authentication in place, and at least two user types with different levels of access. - The platform meets the first condition (a password is required) but not the second — everyone with the password sees and can do exactly the same thing. - On design standards, the roadmap’s next step requires full compliance with Ágora and a full accessibility review (WCAG and European Accessibility Act) — both are now complete. - This is a mixed picture — one full condition met, the other still open — which is best captured as Intermediate rather than Low or Advanced.

5. Capabilities and Features

## 5.1 Functionalities Implemented

| Feature | Status | Notes |
| --- | --- | --- |
| Dimensions overview (flags, filter/sort toolbar) | Implemented | Shows flags for missing data, non-compliance, and under-performance |
| Indicators catalog & detail (gauge, district, channel views, legal basis, technical sheet) | Implemented | Based on real measurement data |
| Service Catalog & detail (innovation suggestions, OPSI case studies) | Implemented |  |
| Dashboard (8 views: KPIs, data completeness, dimension scores, service ranking, channel breakdown, trends, map, compliance scorecard) | Implemented | Built from real data, with sensible messages when data is missing |
| Panorama Estratégico (side-by-side comparison across entities) | Implemented | First page to compare all five entities at once |
| Innovation Resources (OPSI case studies, Accelerator link, Livro Amarelo) | Implemented |  |
| Global Search | Implemented | Searches services, indicators and dimensions across all entities |
| Password protection | Implemented | One shared password; no individual accounts yet |
| Single-indicator history-over-time view | Not yet implemented | Currently switched off everywhere, even though enough real monthly data exists for at least one entity — a quick win still to be claimed |
| Favourites / bookmarks | Out of scope | Deprioritized for this delivery due to the tight timeline, by agreement with OCDE/ARTE — a candidate for a future phase |
| Export, Share, Compare (on the indicator page) | Out of scope | Deprioritized for this delivery due to the tight timeline, by agreement with OCDE/ARTE — a candidate for a future phase |
| “Os Meus Serviços” | Out of scope | Does not exist as a feature in the current build; not part of this delivery’s scope |
| Letting entities upload their own data | Out of scope | Required by the contract, but deprioritized for this delivery due to the tight timeline, by agreement with OCDE/ARTE; data continues to be loaded through the AI-assisted process (Section 3.2), checked by a person at every step |

## 5.2 Analytical Capabilities

- Breaking data down by district, channel, and time.

- Scoring each dimension’s overall performance.

- Ranking services, keeping services with very few responses separate so they don’t skew the ranking.

- Compliance scorecards, all built from real data.

- Panorama Estratégico adds the ability to compare across entities for the first time — the first page to look at the whole system at once, rather than one entity at a time.

- Still missing: AI-assisted analysis or reporting — something OECD’s roadmap lists as a more advanced capability for later.

## 5.3 Alerts and Monitoring

- No automatic notifications — no emails or push alerts.

- Instead: visual flags shown directly on screen, for missing data, legal non-compliance, the lowest-performing services, and scores based on very few responses.

- This is useful but passive — someone has to open the platform to see it.

- Worth being clear with the client: “alerts” today means on-screen flags, not notifications sent out to people.

## 5.4 Innovation Resources

## OPSI case studies and improvement suggestions, organised by dimension, a link to the Innovation Accelerator toolkit, and a link to the “Livro Amarelo” public-complaints platform.

## 5.5 Maturity Assessment – Capabilities

Maturity rating: Intermediate - OECD’s roadmap describes a mid-level set of capabilities: favourite indicators with rankings, missing-data flags, search, and technical comparison sheets. - The platform meets most of this, but favourites don’t work yet. - It already reaches into some more advanced capabilities too — dashboards with rankings/flags/colour-coding, and comparing performance between entities via Panorama Estratégico. - AI-assisted analysis and automatic alerts are both still missing, which is what keeps this area from reaching Advanced.

6. Key Limitations and Risks

- No individual logins. Everyone shares one password; this will need to change before the platform can be rolled out more widely or used by multiple entities independently.

- Some visible buttons remain on screen for features that were deprioritized for this delivery (Export, Share, Compare, and Favourites). To a tester unfamiliar with that decision, these can look broken rather than intentionally out of scope for now — worth considering whether to hide or clearly label them before the next testing round.

- The single-indicator history-over-time view is a quick win still sitting unclaimed: it is switched off everywhere, even though enough real monthly data already exists for at least one entity.

- Compliance data for AT has not been provided, the only entity where this is still the case; its list of services for testing also still needs to be reconfirmed.

- The data-format specification and upload template was delivered as an initial version, but still needs to be updated to reflect the final data before handover (see Appendix A).

- Who owns the hosting and infrastructure has not been decided yet: the website currently runs on a BinaryVoice-owned hosting account, the code is in a BinaryVoice-owned private repository, and the database is on Supabase. A written list of these open questions has already been shared with ARTE, but has not been resolved yet.

- No testing has been done to see how the platform holds up under heavy use; this is fine for now, given the small number of testers, but will need checking before more people or entities join.

7. Recommendations and Next Steps

## 7.1 Structural, for Phase 2 planning

- Plan a proper login system with individual accounts and different permission levels, building on top of the shared password that already exists, so the platform can support more people safely.

- Keep improving the AI-assisted loading process (Section 3.2) so it stays fast and easy to repeat as more entities and data rounds are added.

- Longer term, this could grow into a self-service upload — but a person should always check and approve each step, even then.

- Update the previously-delivered data-format specification and upload template to reflect the final data before handover.

- Answer the open questions about hosting and handover already shared with ARTE (who owns the hosting, how the database gets handed over, who owns the code repository, who holds the passwords and keys, how long support lasts, and what web address the platform will use) before any formal handover takes place.

- Confirm AT’s updated list of services and fill its missing compliance data before the next round of testing.

- Revisit Favourites and Export/Share/Compare for a future phase — both were deprioritized for this delivery by agreement, due to the tight timeline, not dropped as ideas.

## 7.2 Quick wins

- Enable the single-indicator history-over-time view wherever sufficient real monthly data now exists, rather than leaving it disabled platform-wide.

- Hide or clearly label the visible controls for features deprioritized this cycle (Favourites, Export/Share/Compare), so testers don’t mistake “out of scope for now” for “broken.”

## 7.3 Process

## The way the 15 July feedback was handled showed that the project can take on client feedback quickly and keep track of it properly — every item raised was either built, confirmed as already working, or clearly agreed to be left for later. We recommend keeping this up by sharing a short summary of what changed after each round of testing, so OCDE and ARTE can see exactly what was done in response to their feedback.

Appendix A: Terms of Reference — Deliverables Status

The table below maps each deliverable listed in the contract (Terms of Reference) to its current status on the platform, for transparency ahead of handover planning.

| Contract deliverable | Status | Notes |
| --- | --- | --- |
| A working version of the prototype with data-upload capability | Partially met | The platform works and is ready for testing; self-service upload was deprioritized for this delivery, by agreement with OCDE/ARTE, due to the tight timeline — data continues to be loaded through the AI-assisted process described in Section 3.2, checked by a person at every step. |
| A defined data specification (e.g. Excel template or schema) | Partially met | An initial version was delivered; it needs to be updated to reflect the final data before handover. |
| Technical documentation and installation/setup notes | Met | Delivered to ARTE, separately from this repository. |
| A brief handover session or written guidance | In progress | A first written document (listing open questions about hosting and ownership) has been shared with ARTE; a formal handover session or guide has not yet happened. |
| A functioning, test-ready digital tool based on the Figma prototype | Met | The platform is live and working for all five entities; known gaps are listed in Section 6. |
| Implemented service-performance data integration, demonstrated with real or representative datasets | Met | Real data is in use for user-experience, some operational data, and (for 4 of 5 entities) all compliance data. |
| A defined data specification and upload template (Excel) | Partially met | Same status as above. |
| Technical and user-facing documentation sufficient to support user testing | Met | Technical documentation has been delivered to ARTE; the platform itself is also clear to use, with labels, flags, and error messages already in place. |
| Handover materials and/or session, as agreed | In progress | Same as the handover item above. |